## Slide 2: 15th Anniversary Diamond Event
Event Management
Ashley Salvador
Danny Sheng
Emil Stefan
Stephanie Murao

## Slide 3: EVENT DESCRIPTION
  WestJet’s Diamond 15th Anniversary
  Dinner & Dance – By invite only
  Located in WestJet Hangar & Airbus A380
  March 12, 2011 @ 4:30 pm - 12:30 am

## Slide 4: EVENT DESCRIPTION
  Purpose: WestJet Appreciation
  Concept: A fun & sophisticated evening
      Black Tie Event
  Objectives:
    Thank guests for supporting the company
    Provide an exceptional experience

## Slide 6: INVITATION

## Slide 7: EVENT TIMING
  4:30-5:45 – Guests arrive, passed appetizers and cocktails available on Airbus A380.
  5:45-6 – Guests head into airport hangar to find seats and prepare for dinner.
  6 – 8:30 – 5 Course seated meal prepared by Jean-Georges Vongerichten of Market, complete with wine pairings.
  8:30-9:45 – Musical performance from Vancouver local Michael Bublé.
  9:45-10 – Champagne toast. Speech from WestJet CEO Gregg Saretsky.
  10 – 12:30 – Guests are treated to live band and dancing.

## Slide 8: DIAMOND ANNIVERSARY SAMPLE MENU
Created by: Jean-Georges Vongerichten
Appetizer
Tuna Tartare
Avocado, Spicy Radish
Ginger Dressing
Salad
Steamed Shrimp Salad
Tender Greens, Avocado
Champagne Dressing
Soup
Sweet Pea Soup
Entrée
Red Snapper, Nut and Seed Crust
Sweet and Sour Broth
- or -
Grilled Pork Chop Gigante Beans, Peppers Prosciutto Jus
Dessert
Buttermilk Panna Cotta Roasted Apricots Apricot Sorbet
- Vegetarian Menu Available Upon Request -

## Slide 9: EVENT MANAGEMENT
  Event involvement is key
  Variety of tasks

## Slide 10: APPROVALS & CONSULTATION
  Laws, orders & regulations
  Liquor license
  Music license (SoCan)
  Noise
  Local authorities (ex. police)
  Insurance cover

## Slide 11: MARKETING
  Interaction
  Attendance
  Price & Ticket
  Public Relations

## Slide 12: FINANCIAL CONTROL
  Financial Commitment: $541,306
  10% contingency fund
  Budget is completely inclusive of all costs.

## Slide 13: RISK MANAGEMENT
  Identification
  Assessment
  Management of Risks/Hazards

## Slide 14: RISK MANAGEMENT
  Natural Risks
    Fire & heavy rain
  Financial Risks
    Unforeseen costs & fines due
  Mismanagement Risks
    Miscommunication with suppliers & participants
  Technology-related Risks
    Faulty installation & malfunctioning

## Slide 15: EVENT STAGING

## Slide 16: THEME
  15th Anniversary
  Diamond
  White & Silver

## Slide 17: DECOR
  Layout
    Airbus A380: lounge, reception area
    Hangar: Banquet style, dance floor, stage
  Entertainment
    CEO Gregg Saretsky, Champaign band, Michael Buble
  Lighting & Sound
    create an ambience to allow the diamonds to shimmer
    multiple speakers
Notes: <number>
crystal chandeliers, ice sculptures,

## Slide 18: LAYOUT OVERVIEW

## Slide 19: MORE STAGING
  Services
    Overall covered
  Catering
    5 course meal by Jean-Georges
  Waste & Enviro Management
    Implement recycling

## Slide 20: STAFFING
  Positions
    Catering, technical operations, customer relations, media department, etc.
    Hire White Glove Waiters temporary staffing solutions
  Training
  Briefing

## Slide 21: SAFETY & SECURITY
  Inform the police
  Consult with technicians
  Communication

## Slide 22: OPERATIONAL PLAN
  Policies
  Procedures
    Run sheet
  Performance Standards
    Expectations/criteria
  Contingency Plans
  Logistics
    Setup/teardown

## Slide 23: EVALUATION
Measuring Objectives:
    Questionnaires/Guestbook
    Ratio of attendants/invitations
    Track employee performance

## Slide 24: QUESTIONS?